NORTHERN COMMITTEE

Twentieth Regular Session

15 – 16 July 2024

Kushiro, Japan (Hybrid)

Commission’s Climate Change Work Plan and

TOR for the Assessment of CMMs Susceptible to Climate Change Impacts

WCPFC-NC20-2024/WP-04

CLIMATE CO-LEADS’ EXPLANATORY NOTE

This paper provides an update of the work by the Co-leads of the WCPFC climate change workplan which includes:

- Tasks by WCPFC20

- Summary of work by co-leads

- Draft workplan (Attachment A)

- Draft CMM assessment TORs (Attachment B)

Last year’s 19th Northern Committee (NC19) included climate change as a standing agenda item for the first time. Under this agenda item, the NC19  discussed  ways  to incorporate  climate  change  information and  analyses  in  its  work, and specifically how to consider the impacts of climate change on northern stocks. Although there were no recommendations on climate change, general discussion focused on the need to strengthen  cooperation  with  other  RFMOs,  especially  to  allow  for  sharing  of  information, best practices, and  lessons  learned.

The aim of this paper is to consult the Northern Committee (NC) on (3) and (4), particularly on the tasks related to NC.

Tasks by WCPFC20

During WCPFC20, the Commission

- was updated by the SSP on the best available science on potential impacts of climate change on WCPFC fisheries and related ecosystems;

- was updated by the WCPFC Secretariat on work done to incorporate climate change into the management of WCPFC’s fisheries and also on activities in other regional fishery bodies (WCPFC20-2023-12); and

- reviewed the activities of its subsidiary bodies in 2023 to consider climate change and provided advice to its subsidiary bodies to continue their work in 2024 to ensure climate change considerations are adequately reflected in the Commission’s work.

Subsequently, WCPFC20 decided the following tasks for future work:

218. The Commission requested that the Ecosystem and Climate Indicator Report Card be updated and presented annually to the Commission and its subsidiary bodies.

219. The Commission recognised that there is increased importance for the Commission to ensure relevant information and data collection is adequate to support improved and updated understanding by the Commission on the impacts of climate change and implications for management of WCPFC fisheries.

220. The Commission tasked SC and TCC to include as part of the standing agenda item on climate change a review of available data to inform the Commission on climate change impacts to stocks and ecosystems in the WCPO, and the potential effects of climate change on related fishing activities.

221. The Commission tasked the Secretariat with continuing to provide a brief that summarises updates on international and regional fishery bodies (RFB) developments.

222. The Commission requested the Secretariat with the SSP explore the scope and feasibility of undertaking an assessment of active CMMs and to determine specific CMM provisions that may be susceptible to be impacted by climate change, and present the findings to the Science Committee, the Technical and Compliance Committee and the Commission.

223. The Commission recommended co-leads are identified to develop a Commission workplan for addressing climate change on WCPFC fisheries in the Convention Area. The co-leads would use the WCPFC Convention and Resolution 2019-01 as guides for that work. The draft workplan would be discussed and considered by each subsidiary body in 2024, with a view to taking this to WCPFC21 for consideration. The work plan will include, but not be limited to:

a. the scoping and feasibility study of an assessment of CMMs and their susceptibility to be affected by climate change

b. tasking for the SC to explore:

i. how to capture potential effects of climate change on WCPFC fisheries and fish stocks.

ii. mechanisms to test the robustness of existing and candidate management procedures under plausible climate change scenarios within the MSE framework.

c. Engagement with other Regional Fisheries Management Organizations and the Food and Agriculture Organization and their members to discuss shared challenges, leverage available resources, and identify potential pathways for cooperation on addressing climate change effect on fisheries.

224. The co-leads on Climate Change will initially be one representative from the SIDS and one from the USA. The co-leads (RMI and the USA) seek to ensure the workplan addresses the risks of climate change to CMMs and other obligations, taking into account relevant Scientific Committee recommendations and the results of the scoping exercise regarding the assessment of active CMMs’ susceptibility to be impacted by climate change.

225. In developing the Commission’s Climate Change Work Plan, WCPFC20 requested that the co-leads work with members to incorporate ongoing efforts on climate change impact on fisheries from each of the subsidiary bodies and also provide a framework for coordinating Commission-wide work on climate change.

Summary of work by co-leads

The Republic of the Marshall Islands and the United States of America co-lead the work tasked by WCPFC20 (paragraphs 223-225, WCPFC20 Summary Report).

Co-leads met virtually several times between January to March 2024 to set up the work schedule and begin drafting the workplan for addressing climate change on WCPFC fisheries in the Convention Area (“the workplan” hereinafter).

Co-leads have also met with WCPFC Secretariat and the SSP in April. The meeting allowed for reaching a common understanding of responsibilities on the tasks by WCPFC20 and getting views from WCPFC Secretariat and SSP on the proposed approach taken by co-leads on the draft workplan as well as on the scope and feasibility study to assess the current CMMs for climate risk (paragraph 222, WCPFC20 Summary Report) .

In June, co-leads met with the NC Chair to hear his views on an appropriate approach for the discussion of the draft workplan and the draft Terms of Reference for the Climate Assessment of the CMMs during the NC meeting, and also on the proposed tasks assigned by co-leads to the NC and how well these fit within the NC workplan.

The co-lead’s approach includes the socialisation and consultation of the draft workplan with each of the subsidiary bodies, as tasked by WCPFC20 (paragraph 223, WCPFC20 Summary Report).

Draft workplan (Attachment A)

The draft workplan proposed by co-leads is intended to be a living document, as a starting point to set out the tasks and responsibilities to organise and monitor the work on climate change within the WCPFC. The co-leads seek input from the NC during its meeting for the tasks it plans to undertake to incorporate climate change into its work.

Draft Terms of Reference for the CMM assessment (Attachment B)

Following directions from WCPFC20 (paragraphs 222 and 224, WCPFC20 Summary Report) and with the intention to support discussions in relation to the scope, feasibility and technicalities of the assessment of CMMs and their susceptibility to be affected by climate change (cross reference to Secr+SSP paper), co-leads have drafted Terms of Reference for such study. The co-leads seek input from the NC during its meeting on the draft Terms of Reference for the CMM assessment.

Attachment A

WCPFC Co-leads Draft Climate Change Workplan

Objective

Using the WCPFC Convention and Resolution 2019-01 as guides, in response to the WCPFC 20 Outcomes, and upon review and input from each subsidiary body (SB), this work plan will inform the Commission’s efforts to address climate change impacts on WCPFC fisheries in the Convention Area.  The following sections describe actions to be taken by the Commission and its SBs to address climate change impacts on WCPFC fisheries in the Convention Area.

Commission

- Consider and discuss the SB’s recommendations regarding the CMM assessment and continue to discuss appropriate ways to incorporate climate change into the work of the Commission and the SBs.

- Identify and discuss appropriate avenues for incorporating climate change resources available outside the Commission into the work of the commission [in support of executing the work of the Commission]

- Enhance cross-RFMO coordination for climate change discussions, especially with IATTC

- [Additional Commission-level tasks identified by subsidiary bodies, if any.]

Northern Committee

- Coordinate with ISC as it considers how to incorporate climate change advice into management recommendations to NC

- [Additional tasks and objectives developed through discussion with the NC Chair]

- [Additional tasks developed through NC]

Scientific Committee

- Continue the ongoing work with respect to implementing an ecosystem approach to fisheries management (EAFM), including developing the ecosystem indicator report cards; climate and ecosystem modeling; enhancing information on essential habitats for WCPFC target and bycatch species, and on the potential changes to species interactions and spatial overlap in target and bycatch species

- Continue the ongoing work in the SC to agree to climate indicators to track the impact of climate change and ecosystem changes, and develop a process to provide advice to the Commission on the performance of those indicators and the impact of  climate change on WCPFC target stocks, non-target species and other scientific aspects

- Consider how the SC structure might be updated to facilitate climate change work, while still maintaining other core SC functions, and report on these deliberations and any conclusions to the Commission

- SC to include as part of the standing agenda on climate change a review of available data to inform the Commission on climate change impacts to stocks and ecosystems in the WCPO, and the potential effects of climate change on related fishing activities including discussion on the on incorporating climate considerations in the development of harvest strategies and management procedures. The annual review of available data should also provide advice and recommendations to the Commission which identifies information gaps, necessary analyses, and any additional tasks that may further enhance the Commission’s ability to account for climate change impacts on WCPFC fisheries.

- SC to continue to update and discuss the Ecosystem and Climate Indicator Report Card annually

- [Additional tasks and objectives developed through discussion with the SC Chair]

- [Additional tasks developed through SC]

Technical and Compliance Committee

- Consider the outcomes and technical information from the CMM susceptibility assessment, and continue to discuss appropriate ways to incorporate climate change into the work of the TCC.

- TCC to annually review  climate change information to provide the Commission with information, technical advice and recommendations  relating  to  the  implementation  of,  and  compliance  with,  conservation  and management  measures [Convention  Article  14.1(a)].  Advice relating to the assessment of CMM susceptibility to the impacts of Climate Change would provide a first step towards fulfilling TCC’s obligations under Convention Article 14.  TCC’s annual review of available information should also provide recommendations to the Commission identifying information gaps, necessary analyses, and any additional tasks to ensure the Commission’s conservation and management measures contribute to the long-term sustainability of the stocks in accordance with Article 10 of the Convention.

- [Additional tasks and objectives developed through discussion with the TCC Chair]

- [Additional tasks developed through TCC]

Finance and Administration Committee

- Consider and prioritize any Commission or Secretariat requests for supplementary funds or other resources needed to carry out expanded scientific work or technical assessments associated with climate change.

- [Additional tasks and objectives developed through discussion with the FAC Chair]

- [Additional tasks developed through FAC]

Science and Management Dialogues and other WCPFC Intersessional Fora

- Addressing climate change as an underlying question for all WCPFC fora, including the 2024 SMD. Include discussions on the incorporation of climate considerations in the development of management procedures for skipjack and South Pacific albacore.

- Propose convening a 2025 SMD focused on climate change, including discussions on the incorporation of climate considerations in the development of harvest strategies.

- [Additional tasks developed through the SMDs and other WCPFC Intersessional Fora]

The tasks defined in this work plan will be adaptive and flexible to respond to the discussions and needs of the Commission and its Subsidiary Bodies.

Deliverables (from WCPFC20 Outcomes)

218. The Commission requested that the Ecosystem and Climate Indicator Report Card be updated and presented annually to the Commission and its subsidiary bodies.

219. The Commission recognised that there is increased importance for the Commission to ensure relevant information and data collection is adequate to support improved and updated understanding by the Commission on the impacts of climate change and implications for management of WCPFC fisheries.

220. The Commission tasked SC and TCC to include as part of the standing agenda item on climate change a review of available data to inform the Commission on climate change impacts to stocks and ecosystems in the WCPO, and the potential effects of climate change on related

fishing activities.

221. The Commission tasked the Secretariat with continuing to provide a brief that summarises updates on international and regional fishery bodies (RFB) developments.

222. The Commission requested the Secretariat with the SSP explore the scope and feasibility of undertaking an assessment of active CMMs and to determine specific CMM provisions that may be susceptible to be impacted by climate change, and present the findings to the Science Committee, the Technical and Compliance Committee and the Commission.

223. The Commission recommended co-leads are identified to develop a Commission workplan for addressing climate change on WCPFC fisheries in the Convention Area. The co-leads would use the WCPFC Convention and Resolution 2019-01 as guides for that work. The draft workplan would be discussed and considered by each subsidiary body in 2024, with a view to taking this to WCPFC21 for consideration. The work plan will include, but not be limited to:

a. the scoping and feasibility study of an assessment of CMMs and their susceptibility to be affected by climate change

b. tasking for the SC to explore:

i. how to capture potential effects of climate change on WCPFC fisheries and fish stocks.

ii. mechanisms to test the robustness of existing and candidate management procedures under plausible climate change scenarios within the MSE framework.

c. Engagement with other Regional Fisheries Management Organizations and the Food and Agriculture Organization and their members to discuss shared challenges, leverage available resources, and identify potential pathways for cooperation on addressing climate change effect on fisheries.

224. The co-leads on Climate Change will initially be one representative from the SIDS and one from the USA. The co-leads (RMI and the USA) seek to ensure the workplan addresses the risks of climate change to CMMs and other obligations, taking into account relevant Scientific Committee recommendations and the results of the scoping exercise regarding the assessment of active CMMs’ susceptibility to be impacted by climate change.

225. In developing the Commission’s Climate Change Work Plan, WCPFC20 requested that the co-leads work with members to incorporate ongoing efforts on climate change impact on fisheries from each of the subsidiary bodies and also provide a framework for coordinating Commission-wide work on climate change.

Workplan & Schedule

| 2024 Schedule | Activities | Responsible | Action Needed & Remarks |
| --- | --- | --- | --- |
| July - September | Preliminary assessment of two CMMs. Drafting of TORs for the CMM assessment. | Secretariat and SSP | NC20, SC20 and TCC20 to review the preliminary CMM assessment to inform consideration of draft TORs for 2025 Consultancy. |
| TBD | Engagement with other Regional Fisheries Management Organizations and the Food and Agriculture Organization and their members to discuss shared challenges, leverage available resources, and identify potential pathways for cooperation on addressing climate change effects on fisheries | Commission, Secretariat, SSP, and Members | TBD |
| July - September | Present draft work plan to SBs for review and feedback | Co-leads | Consideration of draft work plan by NC20, SC20 and TCC20, with input to co-leads and recommendations to WCPFC21. |
| November - December | Submission and consideration of finalized work plan by WCPFC21 WCPFC21 to discuss the draft TORs for the Assessment of CMM climate susceptibility. | Co-leads | WCPFC21 to consider recommendations from NC20, SC20, and TCC20 on the preliminary CMM assessment. WCPFC21 to consider recommendations from NC20, SC20 and TCC20, and to discuss the climate change workplan. |
| WCPFC21 finalises the on the TORs for the assessment of CMM vulnerability to climate change, depending on the results of the scoping and feasibility study. WCPFC21 agrees on a work plan for addressing climate change on WCPFC fisheries in the Convention Area |  |  |  |

| 2025 Schedule | Activities | Responsible | Action Needed & Remarks |
| --- | --- | --- | --- |
| January - June | Consultancy undertakes assessment in accordance with TORs adopted at WCPFC 21. | Secretariat & SSP | Secretariat hires consultancy and advises on assessment |
| TBD | Engagement with other Regional Fisheries Management Organizations and the Food and Agriculture Organization and their members to discuss shared challenges, leverage available resources, and identify potential pathways for cooperation on addressing climate change effects on fisheries | Commission, Secretariat, SSP, and Members | TBD |
| July - September | Results of the assessment are presented to NC21, SC21, and TCC21. | Subsidiary Bodies and Commission | Develop and discuss recommendations targeting potential decisions for WCPFC22 deliberation. |
| Consult with SPC to schedule | Development of a subsidiary bodies CC work plans and research plans (for SC, a and b can be included in the SC CC research plan) | TBD | TBD |
| TBD | - Explore how to capture potential effects of climate change on WCPFC fisheries and fish stocks - Explore mechanisms to test the robustness of existing and candidate management procedures under plausible climate change scenarios within the MSE framework. | TBD | TBD |
| TBD | Capacity building (for managers mainly) and engagement | Commission with assistance of WCPFC Secretariat and SSP | Potential SMD on Climate Change |
| November - December | Results of the assessment and recommendations from NC21, SC21, and TCC21 are presented to WCPFC22 | Commission | Deliberation of advice from subsidiary bodies with respect to addressing climate change. |
| WCPFC22 agrees on a decision regarding the CMM susceptibility assessment and provides direction to SBs on their tasks to include these findings in their work plans |  |  |  |

| TBD Schedule | Activities | Responsible | Action Needed & Remarks |
| --- | --- | --- | --- |
| TBD | SC tasks/requirements - report card | SC with assistance from SSP | TBD |
| TBD | Engagement and Advocacy | TBD | TBD |

Key Reference Documents for the Work Plan

- WCPFC20 Outcomes, climate change outcomes are paragraphs 18-26

- Resolution 2019-01 - Resolution on Climate Change as it relates to the Western and Central Pacific Fisheries Commission

- WCPFC-TCC19-2023-IP12 - Ecosystem and Climate Indicator Report Card from SC19

- Ecosystem and Climate Indicator Presentation to SC19

Attachment B

DRAFT

Terms of Reference for an Assessment of

CMM Susceptibility to the Impacts of Climate Change

Background

- WCPFC20 affirmed Resolution 2019-01 on Climate Change as it Relates to the Western and Central Pacific Fisheries Commission (WCPFC), by agreeing to develop a work plan (Work Plan) and support an assessment (Assessment) of the susceptibility of WCPFC Conservation and Management Measures to the impacts of climate change in 2024 (WCPFC20 Outcomes):

23. The Commission requested the Secretariat with the SSP explore the scope and feasibility of undertaking an assessment of active CMMs and to determine specific CMM provisions that may be susceptible to be impacted by climate change, and present the findings to the Science Committee, the Technical and Compliance Committee and the Commission.

24a. The Commission recommended co-leads are identified to develop a Commission workplan for addressing climate change on WCPFC fisheries in the Convention Area. The co-leads would use the WCPFC Convention and Resolution 2019-01 as guides for that work. The draft workplan would be discussed and considered by each subsidiary body in 2024, with a view to taking this to WCPFC21 for consideration. The work plan will include, but not be limited to; the scoping and feasibility study of an assessment of CMMs and their susceptibility to be affected by climate change…

- These terms of reference (TOR) define the Scope & Feasibility, Objectives, Process, Tasks, and Time Frame of the Analysis. The TOR also sets out initial expectations of the Commission with respect to the outputs of the Assessment.

Scope

- In consultation with the Work Plan Co-leads from the Republic of the Marshall Islands and the United States (C0-leads), the WCPFC Secretariat and Scientific Services Provider (SSP) have explored the scope of an Assessment as proposed at WCPFC20 (WCPFC20-2023-DP08_Rev02) and detailed in these TOR.

- The scope of the Assessment:

  - is limited to informing (i.e. not advising) the Technical and Compliance Committee, Scientific Committee, and Northern Committee as to whether specific provisions of conservation and management measures (CMMs) of the Commission may be affected by climate change;

  - does not prejudice or have any effect on members’ implementation of obligations arising from specific conservation and management provisions;

  - is not intended to initiate, or result in, renegotiation of CMMs;

  - and will be limited to publicly available information such as adopted CMMs, [and] published climate advice of the SSP and Scientific Committee[, and peer-reviewed scientific literature including species climate vulnerability assessments and research on geographic shifts of species distributions].

Feasibility

- In consultation with the Work Plan Co-leads, the WCPFC Secretariat and Scientific Services Provider (SSP) have explored the feasibility of an Assessment as proposed at WCPFC20 (WCPFC20-2023-DP08_Rev02) and as described in the Objectives, Process, and Tasks of these TOR.

- The Assessment will be completed by [the SSP or]a consultant hired by the Secretariat and completed with a narrow scope as described above. Funding is available to provide compensation for this work.

- Based on available information, the Secretariat and the SSP have determined that the Assessment is feasible as outlined in the TOR and will yield beneficial information to the Commission and its members.

- As a demonstration of this feasibility, the Secretariat and SSP are undertaking a Preliminary Assessment of the tropical tuna and seabird CMMs to present first to NC20, then SC20, and TCC20. Member feedback from this preliminary assessment will inform the Objective, Process, and Tasks of these TORs.

Objective

- The Assessment will:

Review all active WCPFC CMMs and identify specific CMM provisions that may require additional discussion among members as being susceptible to be impacted by climate change.

- The Assessment is not intended to preclude any future consideration, evaluation, or prioritization of any CMM, including those not immediately deemed the most susceptible to climate change impacts.

Process

- The Assessment will:

  - compile available advice from the SSP and Scientific Committee on climate risks to fisheries managed by the Commission;[, and peer-reviewed scientific literature including species climate vulnerability assessments and research on geographic shifts of species distributions].

  - review and analyze active CMM provisions available via the WCPFC website in the context of 10(a); and

  - provide toNC21, SC21 and TCC21 a list of active CMM provisions with an explanation of any identified potential climate vulnerabilities associated with specific provisions.

- The Assessment will be overseen by the WCPFC Secretariat in conjunction with the SSP and will be considered by the Commission and its subsidiary bodies meetings, following the schedule in the adopted WCPFC climate change work plan during the Climate Change agenda item for each meeting.

Tasks

- The Consultant will develop a rubric by which species, geographic considerations, and gear types are generally prioritized by susceptibility through consideration of both sensitivity and exposure to climate change impacts.

- The susceptibility to climate change of fisheries conservation and management has not been explored or discussed by the Commission. As a first step towards focusing the work of members, and without taking on the more complex task of ranking each susceptible provision, this Assessment will categorize CMM provisions as either being “Susceptible” or “Not Susceptible” to climate change.

- The first step will also involve development of definitions for “Susceptible” and “Non Susceptible” based on available science, and this will be the first outcome of the assessment for review by the Scientific Committee.

- The Susceptibility category will consider, but not limited to, whether provisions of WCPFC CMMs are implemented based on:

- certain target of bycatch species,

- specific geographic areas,

- different gear types,

- review period, or

- any mention of climate or climate awareness.

- The Assessment may offer recommendations for further consideration by the Commission as to how to rank or prioritize among the CMM provisions that are identified as “Susceptible” to climate change, but such recommendations will not be implemented in, or as a direct result of, the Assessment.

- The Consultant will complete the tasks in paragraphs 12-17 based on the process in paragraphs 11 & 12.

Timeframe

- The proposed timing for the Assessment and its consideration by the Commission and its subsidiary bodies is as follows:

| Timing | Description |
| --- | --- |
| June - September 2024 | Draft TORs circulated to Members alongside the Preliminary Assessment of the Tropical Tuna and Seabird Measures. |
| January 2025 | Initiate the Consultancy and Assessment. |
| June - September 2025 | Results presented to NC21, SC21, and TCC21 for review and recommendations to the WCPFC22 |
| WCPFC22 (Dec 2025) | Climate change taskings to subsidiary bodies for 2026. |