## Slide 1
Species | Stock | Last Assessment | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Striped marlin | N Pacific | 2023 |  | A |  |  |  | A |  |  | 
 | SW Pacific | 2019 |  |  | A |  |  |  |  | A | 
Swordfish | N Pacific | 2023 |  | A |  |  |  |  | A |  | 
 | SW Pacific | 2021 |  |  |  | A |  |  |  | A | 
Blue Marlin | Pacific | 2021 |  |  |  |  | A |  |  |  | 
Black Marlin | WCPO | Never |  |  |  |  | L/C |  |  |  | 
Sailfish | WCPO | Never |  |  |  |  | L/C |  |  |  | 
Shortbill Spearfish | WCPO | Never |  |  |  |  | L/C |  |  |  | 

## Slide 2
Title | Priority | Start Year | End Year | Comments
Assessment 1) North Pacific striped marlin stock assessment | High | 2023 | 2023 | Completed (2023)- assessment accepted by SC19 (SC19-SA-WP-11 and SC20-SA-WP-12)
Assessment 2) Southwest Pacific striped marlin stock assessment | High | 2024 | 2024 | Completed (2024)– to be evaluated by SC20. SC20-SA-WP-03 and SC20-SA-IP-06
Assessment 2) Southwest Pacific striped marlin stock assessment | High | 2023 | 2023 | Completed (2023) assessment accepted by SC19 (SC19-SA-WP-09 )
Assessment 4) Southwest Pacific swordfish stock assessment | High | 2025 | 2025 | Previous assessment successfully conducted by the SPC. Draft project specification in Appendix 1.
Assessment 5) Pacific blue marlin stock assessment | High | 2026 | 2026 | Previous assessment successfully conducted by the ISC
Assessment 6) Assessment approaches for WCPO black marlin, sailfish and shortbill spearfish | Medium | 2025 | 2025 | Develop conceptual models for each species to identify appropriate modelling approaches for low catch low information assessments. Draft project specification in Appendix 1.

## Slide 3
Title | Priority | Start Year | End Year | Comments
Biology 1) Development of a statistically robust sampling plan for the collection of fisheries dependent biological samples (by sex), including but not limited to age, size frequency data, and genetic samples for WCPO swordfish (north and south). | High | 2024 | 2027 | Completed (2024)- (SC20-SA-IP-13)
Biology 2) Biology of South Pacific striped marlin, blue marlin, black marlin, shortbill spearfish and sailfish in the WCPO from longline fisheries. | High | 2025 | 2028 | Collect samples (fin spines and otoliths) and then undertake age growth and reproductive analyses to get growth and maturity parameters to inform productivity rates of this species. Length-weight and length-length conversion factor data collection for SP striped marlin. Draft project specification in Appendix 1.
Biology 3) Undertake directed longitudinal tagging of Southwest Pacific swordfish to reduce the uncertainty in movement rate. | High | 2025 | 2027 | Develop conceptual models for each species to identify appropriate modelling approaches for low catch low information assessments. Draft project specification in Appendix 1.