## Sheet1
Draft 2006 Work Program and Budget for the TCC (subject to consideration by WCPFC2) | [13 empty] | Attachment I
Date | Meeting | Vessel record | $ | VMS | $ | Observer Programme | $ | Port Scheme | $ | Transhipment | $ | Boarding and Inspection | $ | Catch Reporting | $ | Catch/Statistical Documentation Scheme | $ | TCC Process for formulating and provision of advice to Commission | TCC Process to consider CNM applications | Compliance failure processes | Sanctions process | Cooperation with other organisations | Cooperation with Subsidary bodies e.g. Scientific Committee | Processes for SRF
Dec | WCPFC2 | Urge Members to supply data |  | Commission agrees on VMS functions. Circulates draft specifications and data security for intersessional work. |  | Agree to framework for the RoP. |  | FAO Guidelines accepted as a basis for harmonising. |  | Agree to develop Transhipment Verification Scheme |  | ToR for Inter-sessional (procedures for UNIA implementaton including attempts to address outstanding issues from WGIII draft) |  | Role in catch verification throughout range of species/Convention Area. Monthly BE catch reporting requested |  | Request for background material to assist Commission
Jan | [5 empty] | Advertise OPM
Feb |  | Commission's IT strategy | [9 empty] | Electronic inter-sessional
Mar |  |  |  | Comments on draft specs and data security by email. |  |  |  | Member port State information provided to Secretariat |  | Members provide list of designated ports | [5 empty] | If required, review of catch and trade documentation options (other RFMOs e.g. ICCAT) with focus on BE and draft report/forms templates | 15000
Apr | [9 empty] | Develop procedures to obtain and verify transhipment data - link to work on port State Scheme. Develop procedures for transhipment beyond areas of national jurisdiction Review practice in other RFMOs (ICCAT, etc.) |  |  |  | Possible capacity building for Ind/Phil, SIDS, etc
May |  | Consultations with other RFMOs Call for tender design and implementation of vessel database |  | Revised specs.and data security for adoption by Comm3. |  | OPM on board |  | Inventory of existing practice and gaps analysis | 25000 |  |  | Draft report of the inter-sessional
Jun | [5 empty] | Standards and procedures (consultations with other RFMOs (joint SC/TCC - tender) | 10000
Jul |  |  |  | Secretariat prepares information paper on implementation and operational costs of shortlisted options. Info. Paper discusses cost recovery options. |  | Standard procedures for the RoP. Email consultation with Members. | 20000 | Standardised data collection/documentation for port visits (SPC-OFP/CM)
Aug | SC |  |  | Secretariat prepares draft ToRbased upon revised specs and security with shortlisted implementation options. |  | SC2 |  | SC2 |  | Draft Procedures discussed at SC
Sep | [5 empty] | Audit of existing programs.
Oct | [11 empty] | Final draft of Procedures
Nov
Dec | TCC2/WCPFC3 |  |  | TCC2 considers and advises Comm3 of preferred implementation options, cost recovery mecanism, final ALC specs and data security. TCC revises ToR. Comm3 agrees on above VMS issues and tasks Secretariat to proceed to tender based upon agreed ToR. |  | Standards considered and possibly adopted, coordination described, training needs and certification possibly adopted |  | TCC2 considers harmonised port State model including documentation and possible submission to Comm3. |  | TCC2 considers draft procedure fr submision to Comm3 for possible adoption. |  | TCC2 considers draft procedure for possible submission to Comm3 for possible adoption. |  |  |  | TCC2 considers papers and disusses requirements for subsequent formal establishment of CDS.
Total | 110000 |  | 40000 |  |  |  | 30000 |  | 25000 | [7 empty] | 15000
Feb
Mar
Apr
May
Jun
Jul
Aug | Sc
Sep
Oct | TCC
Nov
Dec | WCPFC4
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug | SC
Sep
Oct | TCC
Nov
Dec | WCPFC5