NORTHERN COMMITTEE

Second Regular Session

11-13 September 2006

Tokyo, Japan

Proposed Work Programme for the Northern Committee

WCPFC/NC2/23 rev.2

13 September 2006

| Work areas | 5-year objectives | 1-year tasks |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2007-2011 | 2007 | 2008 | 2009 | 2010 | 2011 |
| 1. Northern stocks |  |  |  |  |  |  |
| a. Monitor status; consider management action | Review status and take action as needed for: |  |  |  |  |  |
|  | North Pacific albacore | Obtain and review complete assessment (ISC) and consider management action |  |  |  |  |
|  |  | Obtain scientific advice and make recommendations for reference points for NP albacore |  |  |  |  |
|  | Pacific bluefin tuna | Obtain review on the status of the stock (ISC, w/ WCPFC data), as well as reports from CCMs on their domestic management measures, and consider management action | Obtain and review complete assessment (ISC, w/ WCPFC data) and consider management action |  |  |  |
|  | Swordfish | Obtain review on the status of the stock (ISC) and consider management action | Obtain and review complete assessment (ISC) and consider management action |  |  |  |
| b. Data | Achieve timely submission of complete data needed for assessments, formulation of measures, and review of Commission decisions | CCMs participating in the NC submit complete data on fisheries for northern stocks to the Commission |  |  |  |  |
|  |  | Encourage submission to Commission of PBT data from all CCMs and make available to ISC |  |  |  |  |
|  | Consider systems to validate catch data |  |  |  |  |  |
| 2. Non-target, associated, dependent species |  |  |  |  |  |  |
| a. Seabirds | Develop/apply appropriate methods to minimize catch and mortality | Develop recommendation for mitigation measures to be adopted by Commission |  |  |  |  |
| b. Sea turtles | Develop/apply appropriate methods to minimize catch and mortality | NC CCMs submit mitigation research results to the Commission, for compilation by Commission | Review mitigation research results and consider management action |  |  |  |
| 3. Review effectiveness of decisions | Annually review effectiveness of conservation and management measures and resolutions applicable to fisheries for northern stocks | Review effectiveness of NP albacore measure (CMM 2005-03) | Review effectiveness of NP albacore measure (CMM 2005-03) |  |  |  |
| 4. Cooperation with other organisations |  |  |  |  |  |  |
| a. ISC | Develop recommendations to Commission for requests to ISC for assessments, analyses, and advice in support of conservation and management measures |  |  |  |  |  |
|  | Facilitate provision of data needed for assessments to ISC |  |  |  |  |  |
| b. IATTC | Following Article 22.4, consult to facilitate consistent management measures throughout the respective ranges of the northern stocks | Following paragraph 8 of CMM 2005-03, initiate consultation to maintain consistent measures for NP albacore |  |  |  |  |

In the event that the Commission, in accordance with paragraph 5 of Annex I of the Commission Rules of Procedure, adds additional stocks, such as the northern stock of striped marlin, to the list of stocks understood to be “northern stocks”, this work programme will be revised to include periodic status reviews and consideration of management action for such stocks.