|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **South Pacific Albacore** | **Skipjack** | **Bigeye** | **Yellowfin** |
| **2015** | SC provided advice on implications of a range of Target Reference Points for South Pacific albacore. | **Commission agreed an interim Target Reference Point (b).** | Commission tasked SC to determine a biologically reasonable timeframe for rebuilding bigeye tuna to [or above] its limit reference point. |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **South Pacific Albacore** | **Skipjack** | **Bigeye** | **Yellowfin** |
| **2016** | **Commission considered management objectives for the fishery or stock (a).**  **Commission agreed on interim maximum acceptable risk level for breaching LRP (c).**  **Performance indicators and Monitoring strategy (d).**   * SC provided advice on a monitoring strategy to assess performance against reference points. * SC provided advice on a range of performance indicators to evaluate performance of harvest control rules. * Commission tasked SPC/SC to develop interim performance indicators to evaluate harvest control rules.] * [Commission agree to a **monitoring strategy** to assess performance against reference points.] | **Commission considered management objectives for the fishery or stock (a).**  **Commission agreed on interim maximum acceptable risk level for breaching LRP (c).**  **Performance indicators and Monitoring strategy (d).**   * SC provide advice on a monitoring strategy to assess performance against reference points. * SC provide advice on a range of performance indicators to evaluate performance of harvest control rules. * Commission agreed interim performance indicators to evaluate harvest control rules. * [Commission agree to a **monitoring strategy** to assess performance against reference points.] | **Commission considered management objectives for the fishery or stock (a).**  **Commission agreed on interim maximum acceptable risk level for breaching LRP (c).**  **Commission agreed timeframes to rebuild stock to limit reference point.** | **Commission considered management objectives for the fishery or stock (a).**  **Commission agreed on interim maximum acceptable risk level for breaching LRP (c).** |
|  | [Chair to complete brief outline of progress at the end of WCPFC13]:  [Recognised the need for some harvest strategy elements to be adopted as ‘interim’ noting that they be reconsidered as the harvest strategy process develops.  Considered management objectives for the fisheries or stocks and made progress on identifying performance measures for skipjack. For South Pacific albacore …  Commenced some early discussions on the relationship between harvest strategies for the different species and multispecies issues.]  +  + | | | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **South Pacific Albacore** | **Skipjack** | **Bigeye** | **Yellowfin** |
| **2017** | **Agree Target Reference Point (b).**   * Commission agree a **Target Reference Point** for south pacific albacore.   **Develop harvest control rules (e).**  and  **Management strategy evaluation (f).**   * SC provide advice on candidate harvest control rules based on agreed reference points. * Commission consider advice on progress towards **harvest control rules**. | **Develop harvest control rules (e)**  and  **Management strategy evaluation (f).**   * SC provide advice on candidate harvest control rules based on agreed reference points. * Commission consider advice on progress towards **harvest control rules**. | **Agree performance indicators and Monitoring strategy (d).**   * SC provide advice on a range of performance indicators to evaluate performance of harvest control rules. * Commission agree interim performance indicators to evaluate harvest control rules   [SC report on BET status following updated assessment.]  [SC and SPC provide advice to the Commission on the likely outcomes of revised tropical tuna measure.] | **Agree performance indicators and Monitoring strategy (d).**   * SC provide advice on a range of performance indicators to evaluate performance of harvest control rules. * Commission agree interim performance indicators to evaluate harvest control rules |
|  | **Consider management objectives for stocks and fisheries (a).** | | | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **South Pacific Albacore** | **Skipjack** | **Bigeye** | **Yellowfin** |
| **2018** | **Develop harvest control rules (e)**  and  **Management strategy evaluation**  **(f)**   * SC provide advice on performance of candidate harvest control rules. * TCC consider the implications of candidate harvest control rules. * Commission consider advice on progress towards **harvest control rules**. | **Develop harvest control rules (e)**  and  **Management strategy evaluation**  **(f)**   * SC provide advice on performance of candidate harvest control rules. * TCC consider the implications of candidate harvest control rules. * Commission consider advice on progress towards **harvest control rules**. | [SC and SPC provide advice to the Commission on the likely outcomes of revised tropical tuna measure.] | **Agree Target Reference Point (b).**   * SC provide advice on a range of Target Reference Points for yellowfin. * Commission agree a **Target Reference Point** for yellowfin.   **Develop harvest control rules (e).**  **Management strategy evaluation (f).** |
|  |  | | | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **South Pacific Albacore** | **Skipjack** | **Bigeye** | **Yellowfin** |
| **2019** | **Develop harvest control rules (e)**  and  **Management strategy evaluation**  **(f)**   * SC provide advice on performance of candidate harvest control rules. * TCC consider the implications of candidate harvest control rules. * Commission consider advice on progress towards **harvest control rules**. | **Management strategy evaluation**  **(f)**   * SC provide advice on performance of candidate harvest control rules. * TCC consider the implications of candidate harvest control rules. * Commission consider advice on progress towards harvest control rules.   **Commission agree harvest control rules (e)** | **Agree Target Reference Point (b).**   * SC provide advice on a range of Target Reference Points for bigeye. * Commission agree a **Target Reference Point** for bigeye.   **Agree monitoring strategy (d).**  **Develop harvest control rules (e).**  **Management strategy evaluation (f).**   * SC provide advice on a monitoring strategy to assess performance against reference points. * SC provide advice on a range of performance indicators to evaluate performance of harvest control rules. * Commission agree to a **monitoring strategy** to assess performance against reference points.   Commission agree performance indicators to evaluate **harvest control rules** | **Agree performance indicators and Monitoring strategy (d).**   * SC provide advice on a monitoring strategy to assess performance against reference points. * Commission agree to a **monitoring strategy** to assess performance against reference points. |
|  |  | | | |